## Swara Kuddu
SAWRA KUDDU HEP CAT PLAN (Against 26.73 lac allotted from CAMPA funds during 2009-10)
S.No. | COMPONENT | Achieved during 2009-10 |  | 2009-10 Spill over funds Achieved during the 2010-11 |  | 2009-10 Spill over funds Achieved during the 2011-12 |  | Total Achievement upto 2009-10 Funds |  | Funds Alloted for 2010-11 |  | Achievement up to 31.3.2011 |  | 2010-11 Spill over funds Acheved during the 2011-12 |  | Total Achievement upto 2011-12 Funds |  | Funds Alloted for 2011-12 |  | Achieved during the 2011-12 |  | Achieved during the 2012-13 |  | Achievement 2013-14 (upto 31.03.2014) |  | Total Achievement up to 31.03.2014
|  | Phy | Fin. | Phy | Fin. | Phy | Fin. | Phy | Fin. | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin | Phy | Fin
1 | Raising Nursery for 1st year plantation/extension (No. of nurseries) |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 416445 | 1 | 416445 | 0 | 0 | 1 | 416445 | 5 | 575000 | 5 | 575000 | 4 | 183500 | 0 | 0 | 1 | 416445
| Total Nurseries | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 416445 | 1 | 416445 | 0 | 0 | 1 | 416445 | 5 | 575000 | 5 | 575000 | 4 | 183500 | 0 | 0 | 1 | 416445
2 | Forest Conservation & Improvement (in ha.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 |  |  |  |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a) | Afforestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 281400 | 12 | 281400 | 0 | 0 | 12 | 281400 | 0 | 0 | 40 | 938000 | 138 | 2856000 | 193 | 8663400 | 205 | 8944800
| Total afforestation New | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 281400 | 12 | 281400 | 0 | 0 | 12 | 281400 | 0 | 0 | 40 | 938000 | 138 | 2856000 | 193 | 8663400 | 205 | 8944800
i | 1st year maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 136500 | 55 | 206100 | 241.03 | 845700 | 241.03 | 845700
| 2nd year maint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 3rd year maint. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Total Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 136500 | 55 | 206100 | 241.03 | 845700 | 241.03 | 845700
b) | Development of NTFP/ Medicinal Plants | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 234500 | 10 | 234500 | 15 | 382500 |  |  | 0 | 0
| Total NTFP | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 234500 | 10 | 234500 | 15 | 382500 | 0 | 0 | 0 | 0
| Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| 1st year maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 109200 | 22 | 73800 |  |  | 0 | 0
| Total Maintenance | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 109200 | 22 | 73800 | 0 | 0 | 0 | 0
c) | Tree plantation on degraded land | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 40 | 938000 | 0 | 0 |  |  | 0 | 0 | 0 | 0
| Silvi Pastural Plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 234500 | 10 | 234500 | 20 | 296400 |  |  | 0 | 0
| Total Tree plantation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 50 | 1172500 | 10 | 234500 | 20 | 296400 | 0 | 0 | 0 | 0
3 | Pasture Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12.03 | 282250 | 12.03 | 282250 | 0 | 0 | 12.03 | 282250 | 0 | 0 | 12.03 | 109473 | 12.03 | 32481 |  |  | 12.03 | 282250
4 | Soil & Moisture Cons. Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
a) | Stablization of active land slides(in m3.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30000 | 30 | 30000 | 0 | 0 | 30 | 30000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 30 | 30000
b) | Check walls (Km) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 110000 | 10 | 110000 | 0 | 0 | 10 | 110000 | 0 | 0 | 54 | 594000 | 0 | 0 | 0 | 0 | 10 | 110000
c) | Stream bank Treatment | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
d) | River bank stablization | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
e | Repair of old engineering structure (in M3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
f | Soil conservation in forest areas (in M3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
g | Reclamation of state mind areas (in M3) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
h | Const. of Cdams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 54 | 918000 | 0 | 0 | 0 | 0
| Medium | 30 | 303000 | 10 | 101000 | 65 | 535227 | 105 | 939227 | 5.39 | 126500 | 0 | 0 | 3 | 126500 | 3 | 126500 | 54 | 594000 | 0 | 0 | 0 | 0 | 0 | 0 | 108 | 1065727
| Small | 10 | 50500 | 27 | 308123 | 0 | 0 | 37 | 358623 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 37 | 358623
i | Const. of silt detention dams | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
j | Const. of percolation tanks | 0 | 0 | 0 | 0 | 0 |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| Construction of Rain water harvesting structure | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
k | Bench terraching | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 5 | 47500 | 5 | 47500 | 0 | 0 | 0 | 0 | 0 | 0
l | Gully Control | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
1 | Model 1st | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 185000 | 20 | 185000 | 0 | 0 | 0 | 0 | 0 | 0
2 | Model 2 nd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 126500 | 10 | 126500 | 0 | 0 | 0 | 0 | 0 | 0 |  | 15 | 21840
3 | Model 3 rd | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 9 | 99000 | 9 | 99000 | 0 | 0 | 0 | 0 | 0 | 0
m | W/Crates | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 172200 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
n | Const. of contour staggered trenches | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 20 | 80000 | 20 | 80000 | 0 | 0 | 0 | 0 | 0 | 0
o | Vegetative Spurs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 21840 | 25 | 194040 | 0 | 0 | 0 | 0 | 0 | 0
| Total | 40 | 353500 | 37 | 409123 | 65 | 535227 | 142 | 1297850 | 45.39 | 266500 | 40 | 140000 | 3 | 126500 | 43 | 266500 | 143 | 1326040 | 143 | 1326040 | 54 | 918000 | 0 | 0 | 185 | 1564350
5 | Building and Roads | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
6 | Operational Support (Nos.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 12 | 616600 | 0 | 225000 | 0 | 0 | 0 | 0
a) | Publicity,research, training & communication | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
7 | Private land development (Agriculture )- in ha. | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
8 | Wild Life Improvement | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
9 | Eco tourism | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 351750 | 15 | 351750 | 0 | 0 | 15 | 351750 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 351750
10 | Forest Protection (Nos.) | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
11 | Training & Studies | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
12 | Awareness & Publicity | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
13 | Cost of B/Wire all ready purchaed | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447555 |  | 447555 | 0 | 0 | 0 | 447555 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 447555
14 | cost. Of cremetoria | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 3 | 1200000 | 3 | 973208 | 0 | 0 | 0 | 0 | 0 | 0
15 | Maintenance of FRH | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 600000 | 3 | 800000 | 0 | 0 | 0 | 0 | 0 | 0
16 | Maint. Of guard qtrs | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 200000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
17 | computer,photocopier and fax | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 10 | 500000 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
18 | Maint. Machinery | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 2 | 116600 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| M&E | [20 empty] | 0 | 26219 | 0 | 0 | 0 | 0
| Total | 40 | 353500 | 37 | 409123 | 65 | 535227 | 142 | 1297850 | 85.42 | 2045900 | 80.03 | 1919400 | 3 | 126500 | 83.03 | 2045900 | 226 | 5924640 | 265.03 | 6053021 | 320.03 | 5200000 | 434.03 | 9509100 | 659.06 | 12852850
19 | Contingency | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
| GRAND TOTAL | 40 | 353500 | 37 | 409123 | 65 | 535227 | 142 | 1297850 | 85.42 | 2045900 | 80.03 | 1919400 | 3 | 126500 | 83.03 | 2045900 | 226 | 5924640 | 265.03 | 6053021 | 320.03 | 5200000 | 434.03 | 9509100 | 659.06 | 12852850
ABSTRACT
I | Afforestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 24.03 | 563650 | 24.03 | 563650 | 0 | 0 | 24.03 | 563650 | 60 | 1407000 | 72.03 | 1516473 | 185.03 | 3567381 | 193 | 8663400 | 217.03 | 9227050
II | Maint. of Afforestation | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 27 | 245700 | 77 | 279900 | 241.03 | 845700 | 241.03 | 845700
III | Nry. Development | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 1 | 416445 | 1 | 416445 | 0 | 0 | 1 | 416445 | 5 | 575000 | 5 | 575000 | 4 | 183500 | 0 | 0 | 1 | 416445
IV | Soil Conservation Works | 40 | 353500 | 37 | 409123 | 65 | 535227 | 142 | 1297850 | 45.39 | 266500 | 40 | 140000 | 3 | 126500 | 43 | 266500 | 143 | 1326040 | 143 | 1326040 | 54 | 918000 | 0 | 0 | 185 | 1564350
V | Other Ancilliary Works | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 15 | 799305 | 15 | 799305 | 0 | 0 | 15 | 799305 | 18 | 2616600 | 18 | 2389808 | 0 | 251219 | 0 | 0 | 15 | 799305
| Total | 40 | 353500 | 37 | 409123 | 65 | 535227 | 142 | 1297850 | 85.42 | 2045900 | 80.03 | 1919400 | 3 | 126500 | 83.03 | 2045900 | 226 | 5924640 | 265.03 | 6053021 | 320.03 | 5200000 | 434.03 | 9509100 | 659.06 | 12852850 | TRUE

## Abstract
Component wise Progress of works carried out under Sawra Kuddu CAT Plan w.e.f. 2009 to 2013-14 (upto 31.03.2014)
S. No. | Components | Achievements upto previous year |  | Achievement during the year |  | Progressive Achievement
|  | Phy. | Fin. | Phy. | Fin. | Phy. | Fin.
I | Afforestation | 24.03 | 563650 | 193 | 8663400 | 217.03 | 9227050
II | Maint. of Afforestation | 0 | 0 | 241.03 | 845700 | 241.03 | 845700
III | Nry. Development | 1 | 416445 | 0 | 0 | 1 | 416445
IV | Soil Conservation Works | 185 | 1564350 | 0 | 0 | 185 | 1564350
V | Other Ancilliary Works | 15 | 799305 | 0 | 0 | 15 | 799305
| Total | 225.03 | 3343750 | 434.03 | 9509100 | 659.06 | 12852850